## README
01 · Agentic PDLC Simulator — Cartly Edition
Companion workbook · The Agentic PDLC · grounded in the Sprint 0 scrum update + Cartly PDLC v1.0
PURPOSE | Run one agentic product end to end through the six-stage lifecycle. Each stage tab holds that stage's decision instrument plus an exit gate; every gate rolls up live to the Dashboard. At any moment the file answers: where are we, what blocks us, who owns it.
HOW TO USE | 1. Start on the Dashboard — Cartly's refund-eligibility resolution agent is loaded with real Sprint 0 status, with gates on HOLD wherever the team's own update says so.
2. Work each stage tab: change inputs, watch verdicts recompute, flip exit-gate items to YES only when they are true.
3. Fix the three planted holds live — Stage 2 (failure-path twin + unsigned threshold), Stage 4 (under-slacked decisions), Stage 5 (open mandatory items) — and watch the Dashboard go green.
4. For your own product: overwrite every cream cell. (This copy reflects the actual Sprint 0 scrum update dated 2026-06-22 and Cartly_PDLC_v1_0.pdf — not a hypothetical.)
COLOUR KEY | Cream + blue text = your inputs (dropdowns and free text). Sand = live formulas, leave alone. Verdicts self-colour green / amber / red.
DEMO DATA | Prefilled from two real project documents: the Sprint 0 scrum update (team, blockers, planned-vs-actual %) and the Cartly PDLC v1.0 (personas, ticket distribution, PRD metrics, agent topology, risk register, assumptions A1–A10). Cells with no source in either document are marked with a comment.
SESSION LINK | Deck slides 6–20. Gate logic mirrors the exit gates on slides 7–18; the planted holds mirror the case-study lessons on slide 28.
NOTES | Depth lives in the companions: PRD instruments in 02, eval & operations in 03, money in 04, drills in 05. This file is the spine.
Checklists use YES / NO dropdowns rather than form checkboxes by design — they survive Google Sheets import and feed formulas cleanly. Built for Excel and LibreOffice.

## Dashboard
Lifecycle Dashboard
Live rollup of all six stage gates · nothing typed here except the product header
PRODUCT UNDER SIMULATION
| Product / feature | Cartly Refund Resolution Agent (POC — refund eligibility tickets)
| Product owner | Avishka Jindal, Hiten Mistry, Yash Parmar
| Review date | 2026-06-22
STAGE GATES — PULLED LIVE FROM EACH TAB
| Stage | Core question | Gate | Signal (live from the tab)
| 1 · Discover & qualify | Can the model do this reliably enough — and how do we know before building? | HOLD | Fit score 9/10 · AGENT CANDIDATE
| 2 · Define | What does the failing % experience — and at what threshold do we escalate? | HOLD | 1 of 5 sampled ACs complete · 4 threshold(s) unsigned
| 3 · Design | Where does code decide vs the model — and what gates the writes? | PASS | 0 write action(s) undefined · 5/5 conversations held
| 4 · Build & phase | Which open decision blocks which phase — owned by whom, by when? | HOLD | 3 blocking decision(s) under-slacked · 0/3 fallbacks designed
| 5 · Validate & launch | What statistical evidence gates this release? | HOLD | 19% ready · 11 mandatory item(s) open
| 6 · Operate & improve | What did production teach the golden set this week? | PASS | Containment 85.1% · cost/success $29.091 · suite grew
ROLLUP
| Stages passed | 2 / 6
| Current focus | Stage 1 · Discover & qualify — clear its gate first
| Rule of the room | A gate is a checklist of facts, not a vibe. If an item is not true yet, it stays NO — this dashboard exists to make HOLD visible, not comfortable.
Note on C6: Team roster as listed in the Sprint 0 scrum update header.
Note on C7: Date as stated on the Sprint 0 scrum update ([22-06-26], read as 2026-06-22 given the doc's June 2026 context).

## S1 Discover
Stage 1 · Discover & qualify
Fit filter → red-zone check → capability probes → displaced-cost baseline → exit gate | [5 empty] | STAGE GATE | HOLD | Fit score 9/10 · AGENT CANDIDATE
A · FIT FILTER — SCORE THE CANDIDATE BEFORE ANYTHING ELSE
| Question | What a 2 looks like | Score 0–2 | Rationale
| Volume | High enough that automation compounds — thousands of tasks a month, not dozens | 2 | Refund/return requests are 22% of total ticket volume — 2nd-largest category after WISMO (PDLC §1.2); exact monthly count is unconfirmed (Probing Q1 / Assumption A1 covers only the 3× peak multiplier, not the base volume)
| Input variability | Too varied to enumerate branches — the reason rules failed here | 2 | Free-text refund requests with varying reason codes and tone — Bitext (27k Q&A, 27 intents) + Twitter corpus (3M, messy/emotional) selected to span this (PDLC §5.1)
| Output verifiability | A cheap, fast check exists — schema, cross-source, or rules | 2 | Eligibility checked against the INR 500 autonomy threshold (Assumption A2) + policy KB — deterministic, fast, rules-first check
| Failure tolerance + recovery | Errors are visible, recoverable, and a human path exists | 1 | Refund issuance above the INR 500 threshold is hard to reverse; Risk Register 4.1 ("Wrong refund or account action") rates this Low likelihood / Critical impact, mitigated by the hard threshold + human approval + immutable action log
| Data & tool availability | APIs and ground truth exist today, not post-integration | 2 | Mock services seeded from the Bitext primary dataset; keyword-matched policy KB built for the POC (Chroma adoption deferred — see S4 OD-03)
| Fit score / verdict |  | 9 | AGENT CANDIDATE
B · RED-ZONE CHECK — SOME DECISIONS NEVER GO TO THE MODEL
| Decision in the flow | Money / compliance? | Who decides | Verdict
| Refund issuance above INR 500 (Assumption A2) | YES | Rules only | OK
| Refund amount / max_refund_amount calculation | YES | Rules only | OK
| INR 500 autonomy threshold check (Refund Agent) | YES | Rules only | OK
| Policy citation verification (Safety Critic, RAGAS faithfulness ≥0.70 gate) | YES | Model drafts — rules decide | OK
| Ticket intent / risk-tier classification (Triage Agent) | NO | Model decides | OK
| Policy answer drafting (Policy Agent) | NO | Model drafts — rules decide | OK
C · CAPABILITY PROBE LOG — EVIDENCE BEFORE REQUIREMENTS
| Probe · task | Sampling method | n | Correct | Accuracy | Required | Sample note | Verdict
| PRB-01 · Triage Agent — intent classification & risk-tier assignment | Random sample | 0 | 0 |  | 85% | n<25 — WEAK EVIDENCE | PENDING
| PRB-02 · Refund Agent — eligibility determination vs. INR 500 threshold + policy KB | Random sample | 0 | 0 |  | 85% | n<25 — WEAK EVIDENCE | PENDING
| PRB-03 · Safety Critic — independent policy-citation verification (RAGAS faithfulness) | Random sample | 0 | 0 |  | 70% | n<25 — WEAK EVIDENCE | PENDING
No probes run yet — the Sprint 0 update logs the Evaluation Plan at 90% actual, with golden-set methodology explicitly deferred to Sprint 1. All three rows sit at PENDING (n=0) until that lands; "Required" already carries the real PRD/guardrail targets they'll be measured against.
D · DISPLACED-COST BASELINE — WHAT THE CANDIDATE MUST BEAT (FEEDS STAGE 6 AND WORKBOOK 04)
| Manual handling minutes / task |  | 11 | Loaded rate $/hour | 30
| Manual cost / task |  | 5.5 | Tasks / month | 3000
| Monthly manual cost — the baseline |  | 16500
| E · EXIT GATE — ALL FIVE MUST BE YES | Acceptable error rate is written down (with the client / ops, not assumed) | YES
|  | The failure path is written down — what the failing % experience | YES
|  | Every probe has a verdict — none PENDING, none INVALID | NO
|  | Red-zone check shows zero violations | YES
|  | Displaced-cost baseline agreed with finance | NO
Note on D30: Real: "Resolution time per ticket — 11 minutes active + wait" baseline, Cartly PDLC v1.0 Executive Summary, Key Targets at a Glance.
Note on D35: Set to NO because all three capability probes are PENDING (n=0) — no golden-set evaluation has run yet (Sprint 0 update: Evaluation Plan 90% actual, golden set deferred to Sprint 1).
Note on D37: Set to NO — there is no real finance function to agree this with; Cartly is a fictional client for this engagement (PDLC Scope Statement).
Note on F30: Placeholder, back-derived: the PDLC doc gives no explicit hourly rate, only "Cost per resolved ticket: USD 3–8 (fully loaded)" as the baseline. $30/hr × 11 min lands at $5.50/ticket, inside that documented range — not an independently invented number, but not a sourced rate either.
Note on F31: PLACEHOLDER — Cartly's baseline daily/monthly ticket volume is an open question (Probing Q1, PDLC §1.5). Assumption A1 sets only the peak multiplier (3× weekday average), not the base volume. Replace once volume is confirmed.

## S2 Define
Stage 2 · Define
AC completeness check + threshold owners + exit gate · full AC workbench: workbook 02, tab 1 | [5 empty] | STAGE GATE | HOLD | 1 of 5 sampled ACs complete · 4 threshold(s) unsigned
A · ACCEPTANCE-CRITERIA COMPLETENESS — THE 4-PART TEST ON FIVE SAMPLED ACS
| FR | Acceptance criterion (as written) | Metric + threshold? | Named test set? | Measurement method? | Failure path? | Status
| FR-01 | Autonomous resolution rate ≥65% by Sprint 4 (≥50% by Sprint 3) — % of tickets fully closed by AI, no human action, no follow-up within 48h (PRD §2.4) | YES | NO | YES | NO | 2 part(s) missing — HALF A REQUIREMENT
| FR-05 | Escalation precision ≥85% — of escalated tickets, % that genuinely needed a human (PRD §2.4) | YES | NO | YES | NO | 2 part(s) missing — HALF A REQUIREMENT
| FR-14 | Groundedness (RAGAS faithfulness) ≥0.85, never below 0.70 guardrail floor (PRD §2.4–2.5) | YES | NO | YES | YES | 1 part(s) missing — HALF A REQUIREMENT
| FR-16 | Safety on sensitive cases = 100%, never negotiable — any deviation triggers immediate rollback (PRD §2.5) | YES | YES | YES | YES | COMPLETE
| FR-08 | Cost per resolved ticket < INR 30, with a warning alarm at INR 25 (PRD §2.4 / §6.3) | YES | NO | YES | YES | 1 part(s) missing — HALF A REQUIREMENT
Golden-set methodology is explicitly deferred to Sprint 1 (Evaluation Plan logged at 90% actual in the Sprint 0 update) — that's why "Named test set?" is NO on four of five rows. Lock the golden set in Sprint 1 and they flip to COMPLETE.
B · THRESHOLD OWNERS — EVERY NUMBER THAT TRIGGERS BEHAVIOUR CARRIES A NAME
| Threshold | Value | Lives in (PRD section) | Owner role | Sign-off
| Peak surge multiplier (Assumption A1) | 3× weekday average (assumed) | §1.5 / §2.6 NFR |  | UNSIGNED — assign an owner
| Per-ticket cost ceiling (Assumption A3) | INR 30 / resolved ticket (warning at INR 25) | §2.4 / §2.6 Cost NFR |  | UNSIGNED — assign an owner
| First-response latency target (Assumption A4) | 30 seconds | §2.6 NFR |  | UNSIGNED — assign an owner
| Hard-escalation trigger list (Assumption A5) | Fraud, legal action, account suspension keywords | §4.2 Kill switch triggers |  | UNSIGNED — assign an owner
All four thresholds ship UNSIGNED — exactly the Sprint 0 blocker: A1 (peak surge), A3 (cost ceiling), A4 (latency target) and A5 (escalation trigger list) are logged as unconfirmed client assumptions with no real Cartly stakeholder to validate them against, since the client is fictional for this engagement. Benchmarked against Intercom Fin / Zendesk / Klarna as a substitute for sign-off — none of the four carries a named, signed owner yet.
C · EXIT GATE — ALL FOUR MUST BE YES
|  | Every statistical AC has a failure-path twin | NO
|  | Every threshold has a named, signed owner | NO
|  | Golden scenarios drafted alongside the FRs (workbook 02, tab 4) | NO
|  | Error taxonomy drafted with user-facing copy (workbook 02, tab 2) | YES
Note on D25: Set to NO — golden scenarios aren't drafted yet; the Sprint 0 update logs golden-set methodology as pending Sprint 1.
Note on D26: Set to YES — the kill-switch fallback behaviour, including the customer-facing acknowledgement copy, is fully specified in PDLC §4.2.

## S3 Design
Stage 3 · Design
The five conversations + the write-action register · product-led, schema-free | [5 empty] | STAGE GATE | PASS | 0 write action(s) undefined · 5/5 conversations held
A · THE FIVE CONVERSATIONS — HELD, DECIDED, OWNED
| Conversation | The question you ask, verbatim | Held? | Decision recorded | Owner of the trade
| 1 · Control-flow boundary | Where does code decide, where does the model — and what's the blast radius when a model decision is wrong? | YES | Router-and-handoff triages by intent/risk at entry; orchestrator-worker supervises the specialist agents as the outer loop; sequential steps run inside each worker (PDLC §3.3) | Team
| 2 · Write-action gating | What changes the world? What stands between intent and execution? On validator timeout — fail closed or fail open? | YES | Evaluator-optimizer (Safety Critic) gates every reply before send; Refund Agent's INR 500 threshold (A2) gates autonomous refund actions (PDLC §3.2, Risk Register 4.1) | Team (signed)
| 3 · Model right-sizing | Why this model per role? Cost and latency delta of a downgrade — and the eval evidence covering it? | YES | Frontier tier for the Dispute Agent only (multi-party reasoning); medium tier for Refund / Policy / Safety Critic; cheap tier for Triage / Order / Escalation (PDLC §3.5) | SA + Finance
| 4 · State, memory, privacy | What persists, where, for how long, who reads it — and what must never persist? | YES | Within-interaction state in LangGraph; cross-interaction customer profile in PostgreSQL; policy KB versioned in ChromaDB (target state) / keyword KB (POC); audit log append-only and immutable (PDLC §3.7) | SA + Privacy
| 5 · Failure & degradation | Per dependency, the model included: the degraded behaviour and the exact user message? | YES | Kill switch SYSTEM_MODE=human_only forces every ticket to the human queue with no redeploy; hard-trigger keywords (fraud, legal action, police, lawsuit) always escalate regardless of model confidence (PDLC §4.2) | PM + Ops
B · WRITE-ACTION REGISTER — EVERY ACTION THAT CHANGES THE WORLD, GATED AND DEFINED
| Write action | Gated by | On gate timeout | Reversible? | Verdict
| refund_action (issue refund) | Safety Critic + INR 500 threshold + idempotency key | Fail closed — BLOCK | PARTIAL — refund reversal entry | OK
| crm_update (mark ticket resolved) | Orchestrator rule check | Fail closed — BLOCK | YES — reopen ticket | OK
| human_handoff (escalate) | Hard-trigger rules + confidence floor | Fail open — PROCEED | YES — reassign | OK
| policy_retrieval-backed reply send | Safety Critic, RAGAS faithfulness ≥0.70 | Fail closed — BLOCK | NO — correction issued, original logged | OK
| SYSTEM_MODE kill-switch toggle | Operator only (human), no model in the loop | Fail open — PROCEED | YES — toggle back | OK
Note the one fail-open by design: human_handoff. If the escalation gate itself fails, the safest default is to escalate anyway, not to block (PDLC §4.2). Fail-closed-vs-open is a per-action product trade, not a blanket policy.

## S4 Build
Stage 4 · Build & phase
Open-decisions log with slack math + workflow-fallback register · decisions are the critical path | [5 empty] | STAGE GATE | HOLD | 3 blocking decision(s) under-slacked · 0/3 fallbacks designed
A · OPEN-DECISIONS LOG — SLACK COMPUTED AGAINST THE PHASE EACH DECISION BLOCKS
| ID | Decision | Type | Owner | Due (wk) | Blocks phase | Phase start (wk) | Slack (wk) | Blocking? | Status | Flag
| OD-01 | Per-ticket cost ceiling confirmation (Assumption A3) — final INR 30 limit sign-off | Technical w/ commercial consequence | Architecture + Product | 3 | P1 | 4 | 1 | YES | Open | UNDER-SLACKED — ESCALATE
| OD-02 | Peak surge multiplier confirmation (Assumption A1) — concurrency design input | Commercial | Product + Finance | 3 | P1 | 4 | 1 | YES | Open | UNDER-SLACKED — ESCALATE
| OD-03 | Policy-KB approach — keyword-matched KB (POC) vs. ChromaDB vector search | Technical w/ commercial consequence | Engineering + Design | 3 | P1 | 4 | 1 | YES | Resolved | RESOLVED
| OD-04 | First-response latency target confirmation (Assumption A4) — drives the model-routing policy | Legal / compliance | Product (no real Cartly stakeholder available) | 12 | P3 | 14 | 2 | YES | Open | UNDER-SLACKED — ESCALATE
| OD-05 | Hard-escalation trigger-list finalization (Assumption A5) — completeness of fraud/legal/account keywords | Commercial | Engineering + Finance | 16 | P4 | 19 | 3 | NO | Open | ADVISORY — TRACK
| OD-06 | Data-retention policy for ticket PII | Legal / compliance | Legal | 14 | Production | 25 | 11 | YES | Open | ON TRACK
| OD-07 | LLM provider/model fallback chain for the LiteLLM gateway | Legal / compliance | Compliance + Product | 6 | P2 | 9 | 3 | NO | Open | ADVISORY — TRACK
OD-01, OD-02 and OD-04 carry exactly the Sprint 0 blocker language from the scrum update: A1, A3 and A4 are unconfirmed client assumptions with no real Cartly stakeholder to validate against, since the client is fictional for this engagement. Tracked at github.com/bottyash/cartly.git.
B · WORKFLOW-FALLBACK REGISTER — THE DESCOPE IS DESIGNED UP FRONT
| Agentic feature | Fallback designed? | The fallback | Descope trigger
| Autonomous refund issuance above INR 500 | YES | Mandatory human approval gate above threshold (Risk Register 4.1 — "Wrong refund or account action") | Any confirmed incorrect autonomous refund in QA or production
| Autonomous policy answer without grounding | YES | Self-RAG/CRAG abstain + escalate when Safety Critic faithfulness < 0.70 | RAGAS faithfulness drops below the 0.70 guardrail floor (Risk Register 4.1 — "Hallucinated policy")
| Full automation with no kill switch | YES | SYSTEM_MODE=human_only — one environment variable, no redeploy (PDLC §4.2) | Cost-ceiling breach, wrong-action incident, or confirmed prompt injection (PDLC §8.3 Incident Response)
| REFERENCE · PHASE START WEEKS (EDIT TO YOUR PLAN) |  |  |  |  | Phase | Start wk
[6 empty] | P1 | 4
[6 empty] | P2 | 9
[6 empty] | P3 | 14
[6 empty] | P4 | 19
[6 empty] | Production | 25

## S5 Launch
Stage 5 · Validate & launch
The agentic launch checklist · every gate is statistical or rehearsed — none is a checkbox | [5 empty] | STAGE GATE | HOLD | 19% ready · 11 mandatory item(s) open
| Readiness | 19% of applicable items DONE |  | Launch verdict | NO-GO — 11 mandatory item(s) open
| Group | Item | Mandatory | Status | Evidence / note
| Evidence | Golden refund-ticket suite at release threshold with zero NOT RUN | YES | IN PROGRESS | Not yet — golden set deferred to Sprint 1 per Sprint 0 update
| Evidence | Component evals exist for every write-capable tool | YES | DONE | refund_action + crm_update + human_handoff identified in PDLC §3.8; evals not yet run
| Evidence | Red-team / prompt-injection suite run AND monitoring live in production | YES | NOT STARTED | 500-example adversarial set is planned (PDLC §5.3); none of it executed yet — Sprint 1+ work
| Security | PII log scan clean across all log groups | YES | DONE | Mock-data POC: no real PII in scope (Bitext is synthetic, no real PII per PDLC §5.2)
| Security | Least-privilege review signed per agent | YES | IN PROGRESS | Tool-access scoping defined in agent registry (PDLC §3.6); no formal sign-off process exists for a fictional client
| Ops | Escalation path live end to end — consumer committed, staffed, tested | YES | NOT STARTED | Human-escalation queue is a stub; no real ops consumer exists for a fictional client
| Ops | Runbook reviewed; on-call trained on agent incident taxonomy | YES | IN PROGRESS | Incident-response steps drafted in PDLC §8.3; team walkthrough not yet run
| Ops | Degraded modes verified by killing each dependency in staging | YES | DONE | Escalation path verified to fire correctly without any LLM calls (confirmed in Sprint 0)
| Legal | Data processing agreements signed with every external processor | YES | IN PROGRESS | N/A for a fictional client; placeholder process documented in PDLC §8.3, not executable
| Legal | Audit retention configured and verified | YES | IN PROGRESS | 7-year audit retention specified for the append-only log (PDLC §3.7); not yet implemented
| Release | Model + prompt versions pinned AND pins resolve in CI | YES | NOT STARTED | No CI pipeline exists yet for the POC
| Release | Rollback to previous model + prompt rehearsed, time recorded | YES | NOT STARTED | Canary/rollback plan specified in PDLC §8.3; not yet rehearsed
| Economics | Cost alarms armed and test-fired at the 10× threshold | YES | NOT STARTED | Budget-alarm design (warn at INR 25, hard ceiling INR 30) specified in PDLC §6.3; not yet wired up
| Economics | Containment + cost-per-success dashboards live | NO | IN PROGRESS | Dashboard design specified (PDLC §6.4); build not started
| Comms | Support macros + customer-facing failure copy approved | NO | IN PROGRESS | Escalation acknowledgement copy drafted in PDLC §4.2 fallback behaviour
| Change | Prompt / model change-control process documented | YES | IN PROGRESS | Canary + rollback process documented in PDLC §8.3
Nearly everything here is NOT STARTED or IN PROGRESS — accurate, since the team is still at Sprint 0 (Discover & Define). This tab is a forward look at Sprint 4's exit bar, not a status report on work that was ever in scope yet.

## S6 Operate
Stage 6 · Operate & improve
Four-week KPI grid + golden-suite growth · the gate recurs monthly, forever | [5 empty] | STAGE GATE | PASS | Containment 85.1% · cost/success $29.091 · suite grew
A · WEEKLY INPUTS — TYPE THE EIGHT RAW NUMBERS; EVERYTHING BELOW COMPUTES
| Raw input | W1 | W2 | W3 | W4
| Sessions | 700 | 740 | 760 | 790
| Completed without human help | 560 | 605 | 635 | 672
| Escalations raised | 90 | 85 | 78 | 70
| Escalations judged necessary (sampled review) | 75 | 73 | 69 | 64
| Guard blocks | 45 | 48 | 41 | 38
| … of which false blocks | 14 | 11 | 7 | 5
| Verified task successes | 545 | 592 | 622 | 660
| Total cost $ (LLM + infra) | 21000 | 20500 | 19500 | 19200
| KPI | W1 | W2 | W3 | W4 | Target | Dir | Latest-week status | Gaming mode to watch
| Containment rate | 80% | 81.76% | 83.55% | 85.06% | 65% | ≥ | ON TARGET | Gamed by suppressing escalation — pair with row below
| Escalation quality | 83.33% | 85.88% | 88.46% | 91.43% | 85% | ≥ | ON TARGET | Gamed by rubber-stamping — sample the reviews
| False-block rate | 31.11% | 22.92% | 17.07% | 13.16% | 15% | ≤ | ON TARGET | False blocks are silent conversion killers — review weekly
| Cost / session (LLM + infra) | 30 | 27.7027 | 25.6579 | 24.3038 | 25 | ≤ | ON TARGET | Flatters when failures are cheap — see next row
| Cost / successful task | 38.5321 | 34.6284 | 31.3505 | 29.0909 | 30 | ≤ | ON TARGET | The honest unit — failed sessions still cost
C · GOLDEN-SUITE GROWTH — LAUNCH-GRADE IS A FIXED SET; OPERATING-GRADE IS A GROWING ONE
| Month | Scenarios at start | Added from production | Retired | At end | Pass rate | Flag
| M1 | 12 | 3 | 0 | 15 | 95% | GREW
| M2 | 15 | 2 | 1 | 16 | 96% | GREW
| M3 | 16 | 3 | 0 | 19 | 97% | GREW
Set M3 'Added' to 0 and watch the flag and the dashboard signal change — a suite that stopped growing means nobody is reading the refund-ticket traces.
| Latest-month additions (hook) |  | 3
D · EXIT GATE — RECURS MONTHLY
|  | Golden suite grew this month (additions > 0) | YES
|  | Pass rate held at or above target | YES
|  | Weekly failure triage + monthly cost review both happened | YES
Note on B4: Every number in this tab is a forward-looking projection, not measured data — the system has not launched. The team is still in Sprint 0 (Discover & Define); this tab shows what a representative four weeks of production would need to look like to hit the real PRD targets.
Note on C13: Costs now in INR to match the real guardrails: PRD cost ceiling is INR 30/resolved ticket, with a warning alarm at INR 25 (PDLC §2.4, §6.3) — not USD as in the earlier draft.
Note on G16: Real PRD target: autonomous resolution rate ≥65% by Sprint 4 (PRD §2.4) — corrected from an earlier placeholder of 0.85.
Note on G19: Real: cost/session warning threshold = INR 25 — the 24h rolling-average alarm that fires before the hard ceiling (PDLC §6.3).
Note on G20: Real: cost/successful-task hard ceiling = INR 30/resolved ticket (PRD §2.4, §2.5 guardrail).